## Sheet1
Issue # | Summary of Tasks | Estimate (hr) | Coding Effort (hr) | Non-Coding Effort (hr) | Estimator | Implementors
1 | Create home page layout | 1 | 0 | 0.5 | Jacob | Jacob
2 | Design Navigation Bar Component | 1.5 | 1 | 0.5 | Albert | Albert
3 | Implement Footer Section | 1.5 | 1 | 0.5 | Albert | Albert
4 | Create Route Map Page | 2 | 1.5 | 0.5 | Shuwei | Shuwei
5 | Add Interactive Route Markers | 1 | 0.5 | 0.5 | Shuwei | Shuwei
6 | Implement User Authentication | 1 | 1 | 0 | Renjie | Renjie
7 | Add Route Logging Database Schema | 1 | 1 | 0.5 | Renjie | Renjie
8 | Create About Page Template | 1 | 1 | 0 | Preston | Preston
9 | Write Documentation & README | 1 | 1 | 0 | Preston | Preston
10 | Buy Vercel Pro Account-issues | 1 | 1 | 0 | Preston | Preston
11 | Design Add Route Page | 1 | 1 | 0 | Jacob | Jacob
12 | Design Landing page | 3 | 2 | 1 | Albert | Albert
13 | Design Add Run Page | 1 | 2 | 1 | Preston | Preston
14 | Update github.io Page | 0.5 | 0 | 0.5 | Jacob | Jacob
15 | Add M2 updates to github io page | 1 | 0 | 1 | Albert | Albert
16 | integrate add route with database | 1 | 2 | 0 | Jacob | Jacob
17 | integrate routes from database to routes page | 1 | 2 | 0 | Jacob | Jacob
18 | Implement playwright "availability" tests for all pages | 2 | 1.5 | 0.5 | Albert | Albert
19 | Standardize Buttons | 1 | 1 | 0 | Albert | Albert
20 | Create User Data | 1 | 1 | 0 | Renjie | Renjie
21 | Modify Add Form | 2 | 2 | 0 | Jacob | Jacob
22 | create route model in database | 0.5 | 2 | 0 | Jacob | Jacob
23 | Edit Navbar to add New Pages, and Change the Email button | 0.5 | 0.5 | 0 | Renjie | Renjie
24 | Implement Edit Run Page | 3 | 2 | 1 | Albert | Albert
25 | Implement Run Reviews | 2 | 3 | 1 | Renjie | Renjie
26 | Implement Awards | 2 | 2 | 1 | Preston | Preston
27 | Update Global.css | 1.5 | 0.5 | 1 | Shuwei | Shuwei
28 | Implement Find Run Page | 2 | 1 | 1 | Preston | Preston
29 | Create or Design Logo/Icon to replace Run and Route Hub | 1 | 0 | 1 | Albert | Albert
30 | Implement Find Running Buddies | 3 | 2 | 1 | Shuwei | Shuwei
31 | Update Home page layout | 1 | 0.5 | 0.5 | Shuwei | Shuwei
33 | Fix Playwrights to provide tests every merge | 3 | 1 | 2 | Albert | Albert
34 | add remove route | 1 | 0.5 | 0 | Jacob | Jacob
35 | Expand Playwright tests to test more pages | 1 | 1 | 0 | Albert | Albert
36 | Extend Prisma User Model and Add Real Runner Data | 1.5 | 1 | 0.5 | Shuwei | Shuwei
37 | Implement Profile Page | 2 | 3 | 2 | Renjie | Renjie
38 | Style Find Run Page | 1 | 2 | 1 | Preston | Preston
39 | Replace Hardcoded Mock Data in Find Buddy Page With Prisma User Data | 1.5 | 0.5 | 1 | Shuwei | Shuwei
40 | Update Playwright Tests | 2 | 1 | 1 | Albert | Albert
41 | Allow Find Run to Search through database | 3 | 2 | 1 | Albert | Albert
42 | Styling Run Reviews | 1 | 2 | 1 | Renjie | Renjie
43 | Styling Profile Page | 1 | 3 | 2 | Renjie | Renjie